## INSTRUCTIONS
INSTRUCTIONS FOR COMPLETING THE DIAGNOSIS:
1- Complete column E to indicate whether or not the recommended measure has been implemented
2- If the answer is not YES or NO, we can manually fill in column I with the percentage we consider to be fulfilled
3 - Complete column D if the measure is considered Essential (tick Yes) or Recommended, as the system will indicate the necessary dedications for both types of measures. If not applicable, indicate No.
4- The system suggests a number of hours to initiate the tasks, or to start them up, we can adjust it to the reality of the organisation
5- Fill in boxes F2 and G2 with the number of internal or eternal technicians that we consider can work on the implementation of measures, and how many days per week.
6- Indicate the starting date of the possible implementation plan in box A5
7 - The system will provide us with a diagnosis of the organisation's situation, as well as a schedule of dates to complete the mandatory or recommended tasks
Contact details: ana@ccn-cert.cni.es
Version: 2.0

## ANTIRANSOMWARE SECURITY PLAN
[6 empty] | Technicians | Days of the week dedicated to implementation
[6 empty] | 2 | 1
Measure | Planification | Planificación Real | Dedication | Applicable? | Implemented? | Tasks | Who? | Observaciones | % Executed | Normally implemented | Mandatory | Complete
1 | 2020-01-01 | 2020-01-01 | 0 | Yes |  | Preliminary study |  |  |  | 0 | 0 | 0
| 2020-01-01 | 2020-01-01 | 0 |  |  | Kickoff |  |  |  | 0 |  | 0
2 | 2020-01-01 | 2020-01-01 | 2 | Yes | Yes | Kickoff and High-level Planning |  |  |  | 2 | 2 | 2
| 2020-01-01 21:00 | 2020-01-01 21:00 | 0 |  |  | 1. Infection prevention |  |  | 10.53% | 44 | 142 | 266
3 | 2020-01-01 21:00 | 2020-01-01 21:00 |  |  |  | 1.1. Raising awareness among users |  |  | 0% | 0 | 0 | 0
4 | 2020-01-01 21:00 | 2020-01-01 21:00 | 8 | Yes | No | Security Policy: Disclosure and Employee Contracts |  |  | 0% | 0 | 8 | 8
5 | 2020-01-05 09:00 | 2020-01-05 09:00 | 24 | Recommended | No | Planned internal employee training |  |  | 0% | 0 | 0 | 24
6 | 2020-01-15 21:00 | 2020-01-15 21:00 | 8 | Yes | No | Awareness-raising of employees |  |  | 0% | 0 | 8 | 8
7 | 2020-01-19 09:00 | 2020-01-19 09:00 | 24 | Recommended | No | Design and implementation of phishing campaigns |  |  | 0% | 0 | 0 | 24
8 | 2020-01-29 21:00 | 2020-01-29 21:00 |  |  |  | DELIVERABLES: Security Policy Agreements with employees Training content Employee signatures on training Phishing campaign Results |  |  |  | 0 | 0 | 0
9 | 2020-01-29 21:00 | 2020-01-29 21:00 |  |  |  | 1.2. Securing the network environment |  |  | 21.05% | 0 | 0 | 0
10 | 2020-01-29 21:00 | 2020-01-29 21:00 |  |  |  | 1.2.1. Software patches |  |  |  | 0 | 0 | 0
11 | 2020-01-29 21:00 | 2020-01-29 21:00 | 2 | Yes | No | HW and SW patch subscriptions |  |  | 0% | 0 | 2 | 2
12 | 2020-01-30 18:00 | 2020-01-30 18:00 | 10 | Yes | No | Updating critical systems when a security update is received |  |  | 0% | 0 | 10 | 10
13 | 2020-02-04 03:00 | 2020-02-04 03:00 | 24 | Yes | No | Monthly tasks on recovery systems and desktop systems |  |  | 0% | 0 | 24 | 24
14 | 2020-02-14 15:00 | 2020-02-14 15:00 |  |  |  | 1.2.2. Minimise work surface |  |  |  | 0 | 0 | 0
15 | 2020-02-14 15:00 | 2020-02-14 15:00 | 8 | Yes | No | Change of network access based on RBAC (Role Based). |  |  | 0% | 0 | 8 | 8
16 | 2020-02-18 03:00 | 2020-02-18 03:00 | 16 | Recommended | No | Implementation of the Privileged Accounts Management System (PMP). Secure sessions and make them auditable. |  |  | 0% | 0 | 0 | 16
17 | 2020-02-25 03:00 | 2020-02-25 03:00 |  | Yes | No | Control of policies implemented on devices through Antivirus |  |  | 0% | 0 | 0 | 0
18 | 2020-02-25 03:00 | 2020-02-25 03:00 | 20 | Yes | No | Cleaning of PCs (including Java and Flash), restriction of Administrator and process privileges for new software and authorisation plan |  |  | 0% | 0 | 20 | 20
19 | 2020-03-04 21:00 | 2020-03-04 21:00 | 4 | Recommended | No | Enable Browser execution in SandBox (Sandbox) |  |  | 0% | 0 | 0 | 4
20 | 2020-03-06 15:00 | 2020-03-06 15:00 |  |  |  | 1.2.3. Antivirus Protection |  |  |  | 0 | 0 | 0
21 | 2020-03-06 15:00 | 2020-03-06 15:00 | 32 | Yes | Yes | End Point Security for Desktop (more than Antivirus) |  |  | 100% | 32 | 32 | 32
22 | 2020-03-20 15:00 | 2020-03-20 15:00 | 3 | Yes | No | Deploying antivirus on servers |  |  | 0% | 0 | 3 | 3
23 | 2020-03-21 22:30 | 2020-03-21 22:30 | 3 | Yes | No | Antivirus configuration with additional functions (IPS, Device Control) |  |  | 0% | 0 | 3 | 3
24 | 2020-03-23 06:00 | 2020-03-23 06:00 | 0 | Recommended | Yes | Whitelisting and blacklisting in Firewall |  |  | 100% | 0 | 0 | 0
25 | 2020-03-23 06:00 | 2020-03-23 06:00 |  |  |  | 1.2.4. Securing the client workstation and mobile devices (especially notebooks) |  |  |  | 0 | 0 | 0
26 | 2020-03-23 06:00 | 2020-03-23 06:00 | 4 | Yes | No | Block administrator privileges |  |  | 0% | 0 | 4 | 4
27 | 2020-03-25 | 2020-03-25 | 24 | Recommended | No | Configure NAP (Network Access Protection) Policies on servers and a deployment manager |  |  | 0% | 0 | 0 | 24
28 | 2020-04-04 12:00 | 2020-04-04 12:00 | 16 |  |  | 1.2.5. Treatment of e-mails / spam in clients |  |  |  | 0 | 0 | 16
29 | 2020-04-11 12:00 | 2020-04-11 12:00 | 8 | Yes | No | GPO Preventive policies on browsing and client e-mails |  |  | 0% | 0 | 8 | 8
30 | 2020-04-15 | 2020-04-15 | 8 | Recommended | No | Configuring permitted accessories and trusted locations |  |  | 0% | 0 | 0 | 8
31 | 2020-04-18 12:00 | 2020-04-18 12:00 |  |  |  | 1.2.6. E-mail / Spam treatment on servers |  |  |  | 0 | 0 | 0
32 | 2020-04-18 12:00 | 2020-04-18 12:00 | 4 | Yes | Yes | Antispam module activated for Office365 / Other accounts |  |  | 100% | 4 | 4 | 4
33 | 2020-04-20 06:00 | 2020-04-20 06:00 | 8 | Recommended | No | Configure Office365 / Other accounts in a secure environment |  |  | 0% | 0 | 0 | 8
34 | 2020-04-23 18:00 | 2020-04-23 18:00 | 8 | Yes | Yes | SPF implementation mechanism |  |  | 100% | 8 | 8 | 8
35 | 2020-04-27 06:00 | 2020-04-27 06:00 |  |  |  | DELIVERABLES: Notification patches from major HW and SW vendors. Implementation of password management system AV adjusted PCs securisation Implementation of server policies (NAP, GPO...) |  |  |  | 0 | 0 | 0
| 2020-04-27 06:00 | 2020-04-27 06:00 |  |  |  | 2. Reducing the impact/damage of reported infections |  |  | 22.67% | 56 | 104 | 201
36 | 2020-04-27 06:00 | 2020-04-27 06:00 |  |  | No | 2.1. Backup |  |  | 40% | 0 | 0 | 0
37 | 2020-04-27 06:00 | 2020-04-27 06:00 | 16 | Yes | Yes | Implementation of daily backups |  |  | 100% | 16 | 16 | 16
38 | 2020-05-04 06:00 | 2020-05-04 06:00 | 24 | Recommended | No | Implementation of high server availability |  |  | 0% | 0 | 0 | 24
39 | 2020-05-14 18:00 | 2020-05-14 18:00 | 8 | Yes | Yes | Immediate copies of backups should be stored on disconnected media (tape drive). |  |  | 100% | 8 | 8 | 8
40 | 2020-05-18 06:00 | 2020-05-18 06:00 | 4 | Recommended | No | Creation of periodic tasks to evaluate the recovery process (every 3 months) |  |  | 0% | 0 | 0 | 4
41 | 2020-05-20 | 2020-05-20 | 2 | Recommended | No | Encrypt most recent backups |  |  | 0% | 0 | 0 | 2
42 | 2020-05-20 21:00 | 2020-05-20 21:00 |  |  | No | 2.2. Shared networks |  |  | 33.33% | 0 | 0 | 0
43 | 2020-05-20 21:00 | 2020-05-20 21:00 | 16 | Yes | Yes | Access to shared networks based on Roles and Permissions |  |  | 100% | 16 | 16 | 16
44 | 2020-05-27 21:00 | 2020-05-27 21:00 | 2 | Recommended | No | Archive older projects in read-only access |  |  | 0% | 0 | 0 | 2
45 | 2020-05-28 18:00 | 2020-05-28 18:00 | 3 | Recommended | No | Using Access-based Enumeration (ABE) to hide shared files |  |  | 0% | 0 | 0 | 3
46 | 2020-05-30 01:30 | 2020-05-30 01:30 |  |  |  | 2.3. Network segment |  |  | 0% | 0 | 0 | 0
47 | 2020-05-30 01:30 | 2020-05-30 01:30 | 24 | Yes | No | Clients, servers, printers and terminals must be separated in virtual networks |  |  | 0% | 0 | 24 | 24
48 | 2020-06-09 13:30 | 2020-06-09 13:30 | 8 | Recommended | No | Only allowed absolutely necessary communications between VLANs by firewall policies, everything else must be blocked. |  |  | 0% | 0 | 0 | 8
49 | 2020-06-13 01:30 | 2020-06-13 01:30 |  |  |  | 2.4. Secure remote access |  |  | 0% | 0 | 0 | 0
50 | 2020-06-13 01:30 | 2020-06-13 01:30 | 16 | Yes | No | Enable two-factor authentication in Firewall for VPN |  |  | 0% | 0 | 16 | 16
51 | 2020-06-20 01:30 | 2020-06-20 01:30 | 8 | Recommended | No | Monitor remote access to prevent brute force attacks. Review monthly |  |  | 0% | 0 | 0 | 8
52 | 2020-06-23 13:30 | 2020-06-23 13:30 | 16 | Recommended | No | Execute penetration test/vulnerabilities/within the network. |  |  | 0% | 0 | 0 | 16
53 | 2020-06-30 13:30 | 2020-06-30 13:30 |  |  |  | 2.5. Secure use of administrator accounts |  |  | 40% | 0 | 0 | 0
54 | 2020-06-30 13:30 | 2020-06-30 13:30 | 8 | Yes | Yes | Administrator user account are treated as normal user accounts |  |  | 100% | 8 | 8 | 8
55 | 2020-07-04 01:30 | 2020-07-04 01:30 | 8 | Yes | Yes | Separate administrator accounts from administrator purpose |  |  | 100% | 8 | 8 | 8
56 | 2020-07-07 13:30 | 2020-07-07 13:30 | 6 | Recommended | No | Allow 2FA on administrative accounts (PMP) |  |  | 0% | 0 | 0 | 6
57 | 2020-07-10 04:30 | 2020-07-10 04:30 | 8 | Yes | No | Change ordinary users to personal privileged accounts (PMP). Default domain on passwords on admin accounts to be complex and securely stored. |  |  | 0% | 0 | 8 | 8
58 | 2020-07-13 16:30 | 2020-07-13 16:30 | 24 | Recommended | No | Create a new account called "administrator" without privileges like HoneyPot and monitor access attempts. |  |  | 0% | 0 | 0 | 24
| 2020-07-24 04:30 | 2020-07-24 04:30 |  |  |  | DELIVERABLES: Backup Setting ABE enabled VPN mechanism adjustment Password policy and Administrator account implementation |  |  |  | 0 | 0 | 0
| 2020-07-24 04:30 | 2020-07-24 04:30 |  |  |  | 3. Incident response |  |  | 40% | 0 | 24 | 28
59 | 2020-07-24 04:30 | 2020-07-24 04:30 |  |  |  | 3.1. Important steps in descending order |  |  | 0% | 0 | 0 | 0
60 | 2020-07-24 04:30 | 2020-07-24 04:30 | 16 | Yes | No | Define a specific process for incident reporting and response. |  |  | 0% | 0 | 16 | 16
61 | 2020-07-31 04:30 | 2020-07-31 04:30 |  |  |  | 3.2. Information/Communication chain |  |  | 0% | 0 | 0 | 0
62 | 2020-07-31 04:30 | 2020-07-31 04:30 | 8 | Yes | No | Create list of contacts for communication chain. Train |  |  | 0% | 0 | 8 | 8
63 | 2020-08-03 16:30 | 2020-08-03 16:30 |  |  |  | 3.3. Ransom demand |  |  | 100% | 0 | 0 | 0
64 | 2020-08-03 16:30 | 2020-08-03 16:30 | 0 | Yes | Yes | Eliminate any payment option. File complaint if applicable. |  | It is important to take into account extortion that not only demands a ransom for the decryption of files, but also threatens to publish sensitive information that has been exfiltrated from the victim's network. In this sense, the affected company/organisation must file a complaint to avoid any problems arising from the publication of the stolen information (which could expose personal data of clients/users and trigger legal action for violation of the LOPD or similar). | 100% | 0 | 0 | 0
65 | 2020-08-03 16:30 | 2020-08-03 16:30 |  |  |  | 3.4. Prepare report to authorities. |  |  | 0% | 0 | 0 | 0
66 | 2020-08-03 16:30 | 2020-08-03 16:30 | 4 | Recommended | No | Implement a communication mechanism for authorities with final report. |  |  | 0% | 0 | 0 | 4
67 | 2020-08-05 10:30 | 2020-08-05 10:30 |  |  |  | 3.5. Request assistance from external experts |  |  | 100% | 0 | 0 | 0
68 | 2020-08-05 10:30 | 2020-08-05 10:30 | 0 | Recommended | Yes | External provider with security expertise |  |  | 100% | 0 | 0 | 0
| 2020-08-05 10:30 | 2020-08-05 10:30 |  |  |  | DELIVERABLES: Incident response process Communications contact list |  |  |  | 0 | 0 | 0
| 2020-08-05 10:30 | 2020-08-05 10:30 | 0 |  |  | 4. Additional protection mechanisms |  |  | 8.333% | 0 | 0 | 160
69 | 2020-08-05 10:30 | 2020-08-05 10:30 | 16 |  |  | 4.1. Centralised log server |  |  | 50% | 0 | 0 | 16
70 | 2020-08-12 10:30 | 2020-08-12 10:30 | 16 | Recommended | No | Implement a Logging Policy |  |  | 0% | 0 | 0 | 16
71 | 2020-08-19 10:30 | 2020-08-19 10:30 | 50 | Recommended |  | Implement a central log server --> N/A in small companies |  |  | 100% | 0 | 0 | 50
72 | 2020-09-10 07:30 | 2020-09-10 07:30 | 16 |  |  | 4.2. Prevent unwanted software execution |  |  | 0% | 0 | 0 | 16
73 | 2020-09-17 07:30 | 2020-09-17 07:30 | 8 | Recommended | No | Prevent unwanted software execution Prevent script execution. Disable Windows Script Host (WSH). |  | The execution of any command in Powershell and Office suite macros (which are the main infection technique after receiving a phishing email in organisations) is disabled by GPO on all client and server computers that do not require it. | 0% | 0 | 0 | 8
74 | 2020-09-20 19:30 | 2020-09-20 19:30 |  |  |  | 4.3. Enhanced Mitigation Experience Toolkit (EMET) |  |  | 0% | 0 | 0 | 0
75 | 2020-09-20 19:30 | 2020-09-20 19:30 | 16 | Recommended | No | Enable EMET / CryptoPrevent on computers. |  |  | 0% | 0 | 0 | 16
76 | 2020-09-27 19:30 | 2020-09-27 19:30 |  |  |  | 4.4. Ransomware Identification on the File Server |  |  | 0% | 0 | 0 | 0
77 | 2020-09-27 19:30 | 2020-09-27 19:30 | 16 | Recommended | No | Implement Microsoft’s File Server Resource Manager |  |  | 0% | 0 | 0 | 16
78 | 2020-10-04 19:30 | 2020-10-04 19:30 |  |  |  | 4.5. Monitored access to Ransomware Command & Control servers |  |  | 0% | 0 | 0 | 0
79 | 2020-10-04 19:30 | 2020-10-04 19:30 | 6 | Recommended | No | Update monthly the blacklist in the Firewall. |  |  | 0% | 0 | 0 | 6
80 | 2020-10-07 10:30 | 2020-10-07 10:30 |  |  |  | 4.6. Test the emergency case |  |  | 0% | 0 | 0 | 0
81 | 2020-10-07 10:30 | 2020-10-07 10:30 | 8 | Recommended | No | Design a test environment (BCP) |  |  | 0% | 0 | 0 | 8
82 | 2020-10-10 22:30 | 2020-10-10 22:30 | 8 | Recommended | No | Test the BCP |  |  | 0% | 0 | 0 | 8
| 2020-10-14 10:30 | 2020-10-14 10:30 |  |  |  | DELIVERABLES: Extra mechanisms allowed on server (e.g. EMET) Monthly blacklist update process Business continuity plan and testing
| 2020-10-14 10:30 | 2020-10-14 10:30 |  |  |  | Project closure
| 2020-10-14 10:30 | 2020-10-14 10:30 |  |  |  | DELIVERABLES: Final Report
| Total Hours: |  | 657 | Total time for full implementation
|  |  | 540 | Total time for fundamental implementation
[6 empty] | Type of measures | Normally implemented | Mandatory | Complete |  | Porcentaje de dedicaciones
[6 empty] | 1. Infection prevention | 44 | 142 | 266 |  | 40.61%
[6 empty] | 2. Reducing the impact/damage of reported infections | 56 | 104 | 201 |  | 30.69%
[6 empty] | 3. Incident response | 0 | 24 | 28 |  | 4.275%
[6 empty] | 4. Additional protection mechanisms | 0 | 0 | 160 |  | 24.43%
[6 empty] | TOTAL | 100 | 270 | 655 |  | 100%
Percentage of measures
Formulas:
Planificación Real = [Planification]
Planificación Real = [Planificación Real, row above]+[Dedication, row above]/8/G2/H2*7
Planification = [Planification, row above]+[Dedication, row above]/8/G2/H2*7
Note on B5: Start date Project
Note on C5: Start date Project